## KHAC Development Plan
Kilmarnock Harrier & AC - Development Plan |  |  |  | Key | Complete | 1 |  | Trustee Owners Required | 1
[5 empty] | In-Work | 13 |  | Committee Owners Required | 4
[5 empty] | Not started | 4
[5 empty] | N/A | 0
Responsible Primary Ownership in (bold)
| Club Function | Objectives | Task | Deliverable | Trustee Owner | Comm Owner | Timescales (Forecast or Actual) | Status | Summary of Task Completion
| Governance | Club Mission statement and Values | Create clear mission statement and values | Shared understanding of club purpose and ethos | J.Holt |  |  | Complete | Mission Statement established: Kilmarnock Harrier & Athletic Club: where athletes, families, coaches and volunteers work together to bring out the best in themselves and each other, to get fitter, and go further, faster and higher. Communicate to membership - A.Murray
| Governance | Succession Planning | Review current roles and identify areas that are reliant on one individual. Identify areas which require additional support to recruit deputising/supporting roles to assist succession planning. | Ensure succession planning across all roles across club. Role descriptions reviewed. | K.Todd/ G.Short | Comm Owner required |  | In-Work | Proforma return developed and circulated to office bearers Returns being collated.
| Finance | Gift Aid |  |  | A.Murray |  |  | In-Work
| Club Admin | Increase Membership | Support club Committee and Board to increase membership - Identify opportunities for membership growth - Review current capacity (junior and senior) - Promote club at Running events, Leisure Centres, Gyms, Local press and use social media to target more adults into the club - Promote club at school competitions, running events, Leisure Centres, Local press and social media to target more juniors (when required) | Increase Membership (or maintain due to Covid) | A.Bryden | L.Haggarty | 2021-04-01 | In-Work | Apr 2021 target = 420, Status 364 (Oct 2020) - Waiting List reduction - 70 to 30 (Covid dependant) - Senior - 160 to 184 (Jogging Group/Covid Dependant) +15% Target Initiatives: Keep on Running, New jogging group (Feb) Improvements: Joining Survey proposed
| Club Admin | Member Retention | - Implement a retention monitoring programme for existing members - Develop a method to document members who leave the club and survey for reasons why - Create and implement surveys with members who leave the club - Analysis and feedback results and changes to members | Communicate the reasons for athletes leaving and develop initiatives to encourage athlete retention. Present list of recommendations based on the comments and ideas of the membership to the general committee and board | A.Murray | E.Tonner | 2021-04-01 | In-Work | Club surveys have been undertaken via Survey Monkey in the past. Main findings used as content for Club Development Plan.
| Club Admin | Re-establish Club operations due to Covid 19 | Ensure that the club returns to training in a safe environment with minimal risk. | Return to club training. Communicate Covid updates as guidance changes. | E.Tonner | J.Goldie | 2021-06-01 | In-work | Scottishathletics advice followed. Plan created and the club returned on the 3rd Aug 2020. Jim Goldie has been appointed the Covid Co-ordinator to communincate any further Covid changes. (http://www.kilmarnockharriers.com/covid)
| Competition | Provide Sufficient opportunities for Competitions for all age groups and categories | Review all the Competitions we provide as a club - Do we provide enough? - Any gaps in younger age groups | Indentify any gaps? - Increase Opportunities / Additional Club Comps ? | Trustee Owner required | B.Roberton / S.Sharp |  | In-work | As the club has grown in size not all of the junior athletes have the opportunity to compete in the Youth Development League (YDL) therefore the club have entered the CSSAL to give these athletes a chance to compete. All members given opportunity to compete at Indoor League (rotation of athletes where necessary). In-house competitions. Potential participation in Junior Park Run and Cross Country series (Liverpool) to be investigated.
| Competition | Virtual Competition | In light of the recent Covid pandemic review the way the club can hold competitions remotely. Build on kids challenges, Superteams, Virtual 5k's etc. | Deliver a form of virtual competitions to the club calendar. | I.Gebbie | B.Roberton / S.Sharp |  | Not started
| Coaching | Introduce new jogging group | Plan, recruit and organise training for jog leaders to deliver 10 week 'Couch to 5k' programmes throughout the year | Establish a jogging group with trained coaches. - Give a supported introduction to running - Establish the early part of athletics pathway in the club structure - Recruit new members to the club | K.Todd | J.Goldie | 2021-04-01 | In-work | Pathways Development Officer Work Plan contains this task. - 10 Jog Leaders recruited - Plan created - Finance approval agreed by trustees
| Coaching | Coaching Structure | Review and modify the coaching structure (all age groups) to support the needs of the club | Fit for purpose coaching structure which supports the athletics pathway. | E.Tonner | J.Goldie |  | In-work | - Revised junior structure created and in place (Oct'19) - Revised senior structure proposed
| Volunteers | Ensure sufficient level of volunteers for club operation | Map Volunteer structure Canvas for new volunteers - website/email - local press - volunteer recruitment evening | Identify any gaps in volunteer structure Set up monthly sessions (summer) / bi-monthly in winter to attract new volunteers via parent evenings | K.Todd | Comm Owner required |  | In-work | No recruitment evening has been arranged but appeals via the website and facebook. Creating role descriptions may aid volunteer recruitment. New Volunteer Coordinator required. - Big thank you award introduced for Volunteers - New clothing supplied to Volunteers
| Athletes and Welfare | Find out what the membership want ? | Survey to membership - simple short survey, encourage comments | Consolidated list of Feedback. Use Feedabck to target key areas of feedabck and interest. | J.Holt | Comm Owner required | 2021-04-01 | In-work | Google form created for feedback Joining questionnaire proposed
| Athletes and Welfare | Young Athlete education | Engage some of the older junior athletes to increase their athletics education and provide a coaching pathway. | Introduce Young Athletes Coaching Academy | E.Tonner | J.Goldie | 2020-12-01 | In-work | Planning and ongoing management added to Pathways Development Officer Work Plan to deliver this objective. - Young Athletes Coaching Academy agreed by trustees - 11 young athletes recruited - Candidate training underway (5 recently attended EA online Communications course )
| Athletes and Welfare | Clear Communicated Welfare Policy | Review Welfare Policy and procedures to ensure they are fit for purpose. | Communicate Welfare Policy and key contacts to the to membership. | L.Haggarty/ J.Holt | M.Chalmers/ J.Goldie |  | In-work | Policies to be reviewed. Policy to be updated on the website.
| Athletes and Welfare | Increase input from younger members | Establish a young athlete forum where their views and ideas can help shape the future of the club. | Functioning young athlete forum | L.Haggarty/ J.Holt |  |  | Not started
| Facilities and Equipment | Consolidated List of Club Equipment | To produce list of Equipment and canvas coaches to determine the future equipment needs in advance. | Determine equipment required to allow grants to subsidise costs. | I.Gebbie | B.Roberton |  | In-work | Consolidated List required.
| Facilities and Equipment | Enhance stadium facilities | Review current shortfalls and identify plan to improve. | Hosting of National Track and Field Champs. | I.Gebbie | B.Roberton |  | Not started | No stand for spectator seating, poor drainage of infield and planting of trees/bushes for protection from wind identified as improvements.
| Environment and Community | Increase club involvement with our environment | Identify areas where the club could increase our environment | Links with environmental associations and promoting of good environmental practices to our membership | A.Bryden | Comm Owner required |  | Not started | Matt Dodds proposed closer links with our environment at the AGM to have (early suggestions raised were the ‘Keep Scotland Beautiful’ and the Newmilns Regeneration Associations).
| Environment and Community | Increased community involvement | Review engagement with our community and identify opportunities to increase. | Increased presence within our local community. Charity/Sports days etc | A.Bryden | B.Roberton |  | Not started | Ayrshire Hospice Ayrshire Sportsability
| Officials | Ensure sufficient level of officials for club operation | Assess current number and qualifications of officials. Recruit new officials where required. | Adequate number of trained and volunteer officials to support internal and external competitions/league matches. | K.Todd | B.Roberton/ J.Youden |  | Not started

## SA Healthchecker Recommendation
SA Healthchecker - Club Reviews
https://scottishathletics.clubserve.net/
Login: kilmarnockharriers@gmail.com
Pass: Harriers_1887
Oct-2018 - SA Healthchecker Recommendations |  | Oct-2019 - SA Healthchecker Recommendations
Task | Priority | Task | Priority
Consider developing a recreational running group for juniors. | High | Consider developing a recreational running group for juniors. HIGH | High | Recreational Runnning
Consider developing links to local running events. | High | Consider developing links to local running events. HIGH | High | Recreational Runnning
Ensure the governing/management committee represents all stakeholders. | High | Ensure the governing/management committee represents all stakeholders. HIGH | High | Governing / Management Committee
Consider how the committee might recruit more members or share the workload more equitably. | High | Consider how the committee might recruit more members or share the workload more equitably. HIGH | High | Governing / Management Committee
Consider what committee tasks could be delegated to smaller, focused groups. | High | Consider what committee tasks could be delegated to smaller, focused groups. HIGH | High | Governing / Management Committee
Ensure the club maintains contact with those who have irregular training session attendance. | High | Ensure the club maintains contact with those who have irregular training session attendance. HIGH | High | Retention
Ensure the club monitors retention of new members. | High | Ensure the club monitors retention of new members. HIGH | High | Retention
Consider utilising a marketing and communication working group or subcommittee. | High | Consider utilising a marketing and communication working group or subcommittee. HIGH | High | Planning
Ensure the club takes an organised approach to its marketing and communication. | High | Ensure the club takes an organised approach to its marketing and communication. HIGH | High | Planning
Write and implement a photography policy. | High | Write and implement a photography policy. HIGH | High | Policies and Procedures
Consider hiring out club facilities to generate additional revenue. | High | Consider hiring out club facilities to generate additional revenue. HIGH | High | Facilities, Owned & Leased | N/A
Urgent action is required to determine what business rates payments the club should be making. | High | Urgent action is required to determine what business rates payments the club should be making. HIGH | High | Facilities, Owned & Leased
A user agreement with the facility operator can ensure a good working relationship and help minimise issues. | High | A user agreement with the facility operator can ensure a good working relationship and help minimise issues. HIGH | High | Facilities, General
Ensure the club has helpful links to local schools and students. | High | Ensure the club has helpful links to local schools and students. HIGH | High | Community Engagement
Consider creating a facilities working group or subcommittee. | High | Consider creating a facilities working group or subcommittee. HIGH | High | Facilities, General
Ensure the club has guiding documents in place to effectively manage its facilities. | High | Ensure the club has guiding documents in place to effectively manage its facilities. HIGH | High | Facilities, Owned & Leased
Ensure all club roles have written descriptions. | High | Ensure all club roles have written descriptions. HIGH | High | Overview
The club should ensure checks are mad on equipment prior to the start of any training session and/or competition | High | Write and implement an anti-bullying policy. HIGH | High | Welfare
Ensure first aiders are available at all training venues and competitions. | High | Establish codes of conduct for all groups within the club. HIGH | High | Welfare
Write and implement an anti-bullying policy. | High | The club should ensure checks are made on equipment prior to the start of any training session and/or competition. HIGH | High | Health & Safety
Establish codes of conduct for all groups within the club. | High | Ensure first aiders are available at all training venues and competitions. HIGH | High | Health & Safety
Formalize the club's volunteer recruiting process. | Medium | Applications for funding may be submitted for numerous projects e.g. facility development, training volunteers and buying equipment. HIGH | High | Finance
Consider developing further support for adult beginners. | Medium | Explore possible opportunities for the club to utilise Gift Aid and increase revenue. HIGH | High | Finance
Complete a skills gap analysis for all club roles. | Medium | Ensure the club's volunteers have proper leadership. HIGH | High | Volunteers
Ensure all new volunteers and employees are formally inducted. | Medium | Review policies and procedures related to fire safety. HIGH | High | Compliance
Assess the training needs of all club personnel. | Medium | Consider developing further support for adult beginners. MEDIUM | Medium | Recreational Runnning
Provide individualised guidance to all who are new in their club roles. | Medium | Ensure all volunteers are appropriately recognised and rewarded. MEDIUM | Medium | Volunteers
Ensure the club's partnerships are managed effectively. | Medium | Formalize the club's volunteer recruiting process. MEDIUM | Medium | Volunteers
Corporation tax is due on the profit/surplus made from nonmember income. | None | Ensure that club members and the wider community are aware of the club's core values. MEDIUM | Medium | Culture
Review the club's charitable status to benefit from Gift Aid. | None | Publicize the club's mission statement to all club stakeholders, clarifying what it is that the club does. MEDIUM | Medium | Culture
|  | Complete a skills gap analysis for all club roles. MEDIUM | Medium | Overview
|  | Ensure all new volunteers and employees are formally inducted. MEDIUM | Medium | Overview
|  | Assess the training needs of all club personnel. MEDIUM | Medium | Overview
|  | Provide individualised guidance to all who are new in their club roles. MEDIUM | Medium | Overview
|  | Ensure the club's partnerships are managed effectively. MEDIUM | Medium | Community Engagement
|  | Corporation tax is due on the profit/surplus made from nonmember income. None | None | Tax Status
|  | Review the club's charitable status to benefit from Gift Aid. None | None | Tax Status

## KHAC Development Plan - CLOSED
Kilmarnock Harrier & AC - Development Plan - ACTIVITIES CLOSED |  |  |  |  | Key | Complete | 18
[6 empty] | Closed | 6
[6 empty] | In-Work | 0
[6 empty] | Not started | 0
[6 empty] | N/A | 0
| Club Function | Objectives | Task | Deliverable | Trustee Owner | Timescales (Forecast or Actual) | Status | Summary of Task Completion
| Governance | More robust Club Constitution | Review current constitution and propose any changes required | Revised Club Constitution | G.Short | 2017-03-31 | Complete | The constitution has been reviewed an proposals will be put forward for incorporation at the AGM in April 2017. Constitution accepted at 2017 AGM.
| Governance | Data Protection compliance | Review current procedures and modify where required | Ensure Data Protection adherance | G.Short | 2018-03-31 | Complete | Graham to attend Alison Johnston, Lead Policy Officer – Scotland Information Commissioners Office seession on the 5th Oct to aid club Data Protection compliance. Workshop attended 05/10/17. Graham to coordinate a compliant club Data Protection policy Draft policy created and sent to trustees and committee to review (Feb 2018). Policy amended and reviewed 14/03/18. Minor changes proposed and adpotion recommended at next trustee meeting. 25/05/18 - Policy adopted, added to website and communicated to membership
| Governance | Grievance and Dciplinary Procedures | Review current procedures and modify where required | Revised Grievance and Disciplinary Procedures | G.Short | 2018-07-01 | Complete | Draft procedure created (Feb 2018). Procedure presented at 14/03/18 meeting. Procedure to be circulated for comment and adpoted if agreed at next trustee meeting. 25/05/18 - Grievance Procedure adopted, added to website and communicated to membership
| Finance | Robust Financial Planning | Establish Finacial Plan and set budgets for each sub-team to control spend | Communicated budgets to the General Committee sub-groups | A.Murray | 2018-07-01 | Complete | Forecast and budgets for 2016/17 spend were introduced to manage spend throughout the year. The intention would be to separate this into sub-group spend to allow easier financial management. 2018/19 budget to be presented at 18/07/18 meeting
| Finance | Increase efficiency of membership payments | Move to online Membership System | Increase Membership payments by 10% | A.Murray | 2016-11-24 | Complete | Move to online membership system (paysubsonline) was established in Apr 2016. The system incurrs a 4% adminstration levy but the net figure has achived more than our 10% target. A final % can be added here when our financial year ends in 29th Feb. 2016/17 paid Membership increased by 17%.
| Finance | Understand how Gift Aid can be used to benefit the club | Research use of Gift Aid for benefits | Prepare claim for Gift Aid and submit at year end and pepare template for further claims. | A.Murray | 2018-03-01 | Complete | Alasdair Murray completed registration form. KHAC acceptance to HMRC Charities to enable Gift Aid application on 10/10/17 (Ref: 061000040232). Mike Lynch (GBSport) contacted to determine suitable decleration on Membership Form to allow Gift Aid to be claimed. Gift Aid is still ongoing with the % split of what can be viewed as a donation still to be confirmed. Kilbachan AAC split their membership fee by membership and a facility fee. Alisdair to seek advice from scottishathletics on the best way forward.
| Finance | Identify Grants to support Club Projects | Review Grant Aid avaiable by agencies and channel towards projects | Target £2000 of Grant Income annually | A.Murray | 2017-04-01 | Closed | The club have applied for a £10k grant towards the purchase of new club equipment. This has been completed and sent to the review board. We hope to have a response by Mar 2017 and if successful commence spending in the next financial year.
[6 empty] | 2018-04-01 | Closed | No current projects identified
[6 empty] | 2019-04-01 | Closed | No current projects identified
[6 empty] | 2020-04-01 | Closed | No current projects identified
| Finance | Club Sponsorship | Approach companies to gauge interest for club sponsorship - Coaches Clothing - Sponsored Event - Team Kit etc | Increased Sponsorship Income | A.Murray | 2018-03-31 | Closed | Not required
| Club Admin | Increase Membership | Support club Committee and Board to increase membership - Identify opportunities for membership growth - Review current capacity (junior and senior) - Promote club at Running events, Leisure Centres, Gyms, Local press and use social media to target more adults into the club - Promote club at school competitions, running events, Lesiure Centres, Local press and social media to target more juniors (when required) | Increase Membership by 10% (5% annually thereafter) | C.Glencorse | 2017-04-01 | Complete | Tue/Thur 7pm Begineers group started by our Business Development Officer to increase senior membership. Membership increased by 17% (from 435 to 508).
[6 empty] | 2018-04-01 | Complete | Re-baseline due to monthly memberships. 411 set as new target.
| Club Admin | Improve Membership Process | Online process to register, organise inductions and payment. - Currently lots of emails need to be ansered regarding joining - Make kilmarnockharriers.com/join us web page main point to register and give all information (reduced quantity of emails) | Implement path to join via website, automated emails for key information through to payment. | E.Tonner | 2016-09-30 | Complete | Online process in place for joining and automated email created to direct potential new athletes to Run, Jump and Throw whilst on the waiting list. Induction, Former Members/Volunteer databases added.
| Club Admin | Member Retention | - Implemement a retention monitoring programme for existing members - Develop a method to document members who leave the club and survey for reasons why - Create and implement surveys with members who leave the club - Analysis and feedback results and changes to members | Communicate the reasons for athletes leaving and develop initiatives to encourage athlete retention. Present list of recommendations based on the comments and ideas of the membership to the general committee and board | C.Glencorse | 2017-03-01 | Closed | A 'Former Members' category has been created on our membership database. This also includes field for 'date left' and 'Reason for Leaving' fields. 'Training Night' and 'Group' have also been added to the main database to determine if a specific evening of group has a low retention rate and could be improved. This can be reviewed in Mar'17 and an email sent to those who have not given a reason to determine whether there may be some relevant feedback for the club to improve.
| Competition | Competition Calendar | Develop a well communicate Calendar of Club competitions and Events - Online Calendar, Social Media, Fridge calendar ??? | Clear communicated events calendar for membership | E.Tonner | 2016-11-24 | Complete | Teamapp created to give app calendar of main events to give members/parents a forward view of all events.
| Coaching | Ensure fit for Purpose Coaching Structure | Compare current coaching structure with membership to ensure all areas are provided for within capacity | Identify Gaps. Re-organise and recruit additional coaches as neccesary | E.Tonner | Ongoing | Complete (ongoing) | First pass identified the need for Beginners Group for a Tue/Thur evening which could lead to groups being created for lead up to the roonthe toon 10k event. Pathways Development Officer Work Plan to contain this ongoing action.
| Coaching | Increase Coaches Skills and Knowledge | Encourage coaches to increase there coaching qualifications - Progress to next coaching level - CPD - Coach Mentoring | Increase coaching expertise. Offer Increased level of coach educational to our coaches. Through further courses or mentoring. | C.Glencorse | Ongoing | Complete (ongoing) | Coaching Lead actively promoting Coaching courses and CPD to current coaches. Pathways Development Officer Work Plan to contain this ongoing action.
| Coaching | Improve coaching, education and coordination of groups | Explore whether we could employ a Head Coach - Job Description - Finance Required - Identify Line Manager(s) - Create Initial Plan | Business case to employ Head Coach and Role Description | E.Tonner | 2017-06-30 | Complete | Scottishathletics have provide some job specifications of similar roles for other clubs. A job description for our club has been prepared. Scottishathletics Partnership Agreement agreed and recruitment process commenced.
|  |  |  | Recruitment and Work Plan for Pathways Development Officer | E.Tonner | 2018-01-01 | Complete | Job spec completed and advertised on 13/07/17. No applicants received for post on closing date (14/08/17). Job to be re-advertised. Job re-advertised on 05/09/17 and 2 applicants received on closing date 28/09/17. Interviews to take place 13/10/17. Interviews completed and role filled. Start date 08/01/18. Work Plan to be completed for commencement of Post.
| Volunteers | Increase knowledge and skills of volunteers | Consolidate and create skills database that can be accessed by volunteers. Communicate and encourage volunteers to update over time. | Up to date volunteers skills matrix to help identify coach education and skills gaps. | E.Tonner | 2018-03-30 | Complete | A volunteers database has been created within our online membership database.
| Athletes and Welfare | Find out what the membership want ? | Survey to membership - simple short survey, encourage comments | Consolidated list of Feedback. Use Feedabck to target key areas of feedabck and interest. | C.Glencorse | 2016-11-01 | Complete | An online survey (survey monkey) was created and distributed to the membership to canvas their views. These were reviewed concluding Communication, Coaching and Competition as the main priorities.
[6 empty] | 2018-04-01 | Complete | No. off uses of trial software has expired. Colin to look at costs for a licence. Survey conducted, largely postive comments. Confusion exists over competition strategy and selection policies.
| Athlete Pathway | Schools competition pathway to club athletics | Review alignment of local EA Schools competions and schools Physical Education curriculum with national schools competitions i.e Align Schools Cross Country in Jan/Feb before Scottish Schools in March etc (Ayrshire Schools CC is generally in October but Scottish Schools is in March) | Achieve closer alignment of local EA Schools competitions and Physical Education curriculum to national schools competitions | G.Short | 2017-12-01 | N/A | This has been raised at the Buisness Development Officer Steering Group Meetings. EA Active Schools have an action to influence stronger alignment of the schools competitions. A copy of the scottish schools major competitions has been provide to EA Active Schools via scottishathletics. TRANSFER TO EAAP. Now contained within Club Together officer work plan.